## Sprint 2 burndown chart
Sprint Tasks (Sprint Backlog) | Week 1 Oct. 23-29 | Week 2 Oct. 30-Nov.5 | Week 3 Nov. 6-12 | Week 4 Nov. 13-19 | Week 5 Nov. 20-26
Manager Login | 5 | 5 | 0 | 0 | 0
Manager Student Management | 10 | 10 | 10 | 0 | 0
Manager Teacher Management | 2 | 2 | 2 | 0 | 0
Manager Course Management | 2 | 2 | 2 | 0 | 0
Teacher Grade Statistics | 10 | 10 | 10 | 5 | 0
Teacher Grade Short Questions | 10 | 10 | 10 | 5 | 0
Question Entity Implementation | 0 | 1 | 10 | 0 | 0
Exam Entity Implementation | 0 | 1 | 10 | 0 | 0
Teacher Question Management UI | 0 | 1 | 0 | 5 | 0
Teacher Exam Management UI | 0 | 1 | 0 | 5 | 0
Teacher Registration UI | 0 | 1 | 0 | 5 | 0
Teacher Login UI | 0 | 0 | 0 | 5 | 0
Task 2 Unit Testing | 0 | 0 | 0 | 0 | 7
Task 2 JavaDoc | 0 | 0 | 0 | 0 | 7
Student Login UI | 2 | 2 | 2 | 0 | 0
Student Registration UI | 5 | 5 | 5 | 0 | 0
Student Start Exam UI | 10 | 10 | 10 | 10 | 0
Student Grade Statistics UI | 7 | 7 | 7 | 7 | 0
Task 1 Unit Testing | 7 | 7 | 7 | 7 | 0
Task 1 JavaDoc | 3 | 3 | 3 | 3 | 0
| 73 | 78 | 88 | 57 | 14